## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) | [10 empty] | Period 1 | Period 2 | Period 3 | Period 4 | Period 5
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS | [37 empty] | Thurs | Friday | Saturday | Sunday | Monday
[6 empty] | Fri | Sat | Sun | Mon | Tue | Wed | Thurs
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project brainstorm & research | 1 | 2 | 1 | 2 | 100%
Project statement of work | 3 | 1 | 4 | 1 | 100%
Backend code | 4 | 5 | 4 | 2 | 100%
Frontend code | 5 | 1 | 5 | 2 | 100%
Creating first working prototype | 5 | 1 | 5 | 1 | 100%
Developing working prototype | 5 | 2 | 5 | 3 | 100%
Design presentation/powerpoint | 6 | 1 | 7 | 1 | 100%
Record presentation | 7 | 1 | 7 | 1 | 100%